## Product Backlog
Project Name | School Management And Reporting Tool (SMART)
Product Name: | SMART School | [6 empty] | Complete Fields in Green!!!
Team ID: | Solutions
| Team Member Name | [5 empty] | Initials | Student ID
Required | Shivam Patel | [5 empty] | SNP | 1001707265
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 27 |  |  |  | Total | Total number of features (in column H)
1 | 22 | 5 |  |  | 1 | Total features left at the end of Sprint #1
2 | 15 | 7 |  |  | 2 | Total features left at the end of Sprint #2
3 | 11 | 4 |  |  | 3 | ...and so on
4 | 10 | 1
5 | 9 | 1
6 | 8 | 1
©2016-2021 by George F. Rice
This work is licensed under a Creative Commons Attribution 4.0 International License. | [6 empty] | Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Features
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a(n)… | I want to... | So that I can… | Notes
PERSON | 1 | 1 |  | 13 | 1 | Finished in Sprint 1 | Administrator | Track people’s names and email addresses | Find and contact them | Need a Person base class with to_string / operator<< name and a full_info method
STUDENT | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Administrator | Track students by grade | Verify students’ progress | Need a Student derived class that includes the grade level (1-12)
PARENT | 3 | 1 |  | 3 | 1 | Finished in Sprint 1 | Administrator | Track parents | Coordinate on student progress | Need a Parent derived class
RELATE | 4 | 1 |  | 5 | 1 | Finished in Sprint 1 | Administrator | Associate each student with parents bidirectionally | Know which parents to contact | Mutual aggregate relationship
CLI | 5 | 1 | 25 | 13 | 1 | Finished in Sprint 1 | Administrator | Basic command line user interface | Verify the system before moving to a GUI | This is cli.cpp for sprint 1 only (optional for bonus points)
WINDOW | 6 | 2 |  | 13 | 2 | Finished in Sprint 2 | All | Use a windowed rather than command line interface | Use SMART more intuitively | Create a main window with a menu bar, data area, and status bar
D_STUDENT | 7 | 2 |  | 8 | 2 | Finished in Sprint 2 | Administrator | Create students via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
DISPLAY | 8 | 2 |  | 5 | 2 | Finished in Sprint 2 | Teacher | See all current data in the main window | Keep up with students | Display full_info for students and parents in a table in the data area
D_PARENT | 9 | 2 |  | 5 | 2 | Finished in Sprint 2 | Administrator | Create parents via dialogs | Conveniently enter the data | Series of dialogs, one per constructor parameter, is OK
D_RELATE | 10 | 2 |  | 8 | 2 | Finished in Sprint 2 | Administrator | Relate students to parents via dialogs | Conveniently enter the data | Dialog listing students and entering index, then same for parents
NEW | 11 | 2 |  | 2 | 2 | Finished in Sprint 2 | Administrator | Clear all data | Start a new school | Simply clear all elements from the vectors
SAVE | 12 | 3 |  | 13 | 3 | Finished in Sprint 3 | All | Write the data to persistent storage | Don’t have to re-enter data | See Lecture 15 for an object-oriented strategy to create the file format
LOAD | 13 | 3 |  | 8 | 3 | Finished in Sprint 3 | All | Load data for a school from persistent storage | Don’t have to re-enter data | Select file via a file chooser dialog
SAVEAS | 14 | 3 |  | 8 | 3 | Finished in Sprint 2 | Administrator | Save data to a different filename | Create backups or baselines for new schools | Select filename via a file chooser dialog
TOOLBAR | 15 | 3 |  | 5 | 3 | Finished in Sprint 3 | All | Use the major features via a toolbar | Point and click | Suggest using the Nim game’s toolbar as a baseline
ABOUT | 16 | 3 |  | 1 | 3 | Finished in Sprint 3 | Administrator | Display an About dialog with creator and version | Quickly determine which version is installed | Use Gtk::AboutDialog
COURSE | 17 | 4 |  | 21 | 4 | Finished in Sprint 5 | Administrator | Track students by grade and subject | verigy their class
SEMESTER | 18 | 4 |  | 8 | 4 | Finished in Sprint 4 | Administrator | Track students semester | to verigy what semester class they are in
SECTION | 19 | 4 |  | 5 | 4 | Finished in Sprint 5 | Administrator | Track students by their course, semester and year | to verify students details
20
21
22
SUBJECT | 23 | 5 |  |  | 5 | Finished in Sprint 5 | Administrator | assign subjects to students | see what classes they are taking for semester
TEACHER | 24 | 5 |  | 21 | 5 | In Test | Teacher | see who are the teachers in the school | see what class they teach
GRADE | 25 | 5 |  | 5 | 5 | Finished in Sprint 5 | Administrator | assign grade to students | to see their report
TRANSCRIPT | 26 | 5 |  | 8 | 5 | In Test | Administrator | assign transcript of a student | to see their academic performance
ITERATORS | 27 | 5 |  | 8 | 5 | Finished in Sprint 5
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2021-03-02 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-09
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 10
Day 1 Left | 7 | 3
Day 2 Left | 7 | 0
Day 3 Left | 0 | 7
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Note: Due to the late project start, the results of this sprint will be provided to you (although you may use your own solution if you prefer)
Task ID | Feature ID | Assigned To | Task | Status | Notes
1 | PERSON |  | Code person.h | Completed Day 1
2 | PERSON |  | Code person.cpp | Completed Day 1
3 | PERSON |  | Test compile Person class | Completed Day 1
4 | STUDENT |  | Code student.h | Completed Day 3
5 | STUDENT |  | Code student.cpp | Completed Day 3
6 | STUDENT |  | Test compile Student class | Completed Day 3
7 | PARENT |  | Duplicate Student to Parent | Completed Day 3
8 | PARENT |  | Remove grade, update to_string() and full_info() | Completed Day 3
9 | PARENT |  | Test compile Parent class | Completed Day 3
10 | RELATE |  | Build with example code and verify | Completed Day 3
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2021-03-09 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-23
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 13 | 0
Day 2 Left | 13 | 0
Day 3 Left | 13 | 0
Day 4 Left | 13 | 0
Day 5 Left | 13 | 0
Day 6 Left | 13 | 0
Day 7 Left | 0 | 13
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WINDOW |  | Baseline main.cpp from nim | Completed Day 7
2 | WINDOW |  | Update Makefile for gtkmm | Completed Day 7
3 | WINDOW |  | Baseline Mainwin class from nim | Completed Day 7
4 | D_STUDENT |  | Baseline EntryDialog class from Lecture 14 | Completed Day 7
5 | WINDOW |  | Create menu for SMART in Mainwin class | Completed Day 7
6 | DISPLAY |  | Add display label, vectors, and show_data method | Completed Day 7
7 | D_STUDENT |  | Write on_new_student_click using EntryDialog | Completed Day 7
8 | D_PARENT |  | Write on_new_parent_click using EntryDialog | Completed Day 7
9 | D_RELATE |  | Write on_student_parent_click using EntryDialog | Completed Day 7
10 | WINDOW |  | Add Easter egg to support testing and demos | Completed Day 7
11 | WINDOW |  | Refactor: select, select_student, and select_parent methods | Completed Day 7
12 | WINDOW |  | Test and improve error handling | Completed Day 7
13 | WINDOW |  | Backport bug fixes from P07 | Completed Day 7
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2021-03-23 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-03-30
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 13 | 0
Day 2 Left | 9 | 4
Day 3 Left | 5 | 4
Day 4 Left | 5 | 0
Day 5 Left | 5 | 0
Day 6 Left | 5 | 0
Day 7 Left | 0 | 5
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | PERSON |  | code person.h | Completed Day 2
2 | PERSON |  | code person.cpp | Completed Day 2
3 | STUDENT |  | code student.h | Completed Day 2
4 | PARENT |  | code parent.h | Completed Day 2
5 | STUDENT |  | code student.cpp | Completed Day 7
6 | PARENT |  | code parent.cpp | Completed Day 7
7 | DISPLAY |  | add icons in the toolbar | Completed Day 3
8 | SAVE |  | add save to file menu | Completed Day 3
9 | SAVEAS |  | add save as to file menu | Completed Day 3
10 | ABOUT |  | add about to help menu | Completed Day 3
11 | SAVEAS |  | code save_as method in mainwin.cpp | Completed Day 7
12 | SAVE |  | code save method in mainwin.cpp | Completed Day 7
13 | LOAD |  | code on_open_click method in mainwin.cpp | Completed Day 7
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-04-06 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-13
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 8
Day 1 Left | 8 | 0
Day 2 Left | 8 | 0
Day 3 Left | 8 | 0
Day 4 Left | 8 | 0
Day 5 Left | 8 | 0
Day 6 Left | 8 | 0
Day 7 Left | 0 | 8
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SEMESTER |  | code semester.h and semester.cpp | Completed Day 7
2 | TOOLBAR |  | add icons for new course and new section to toolbar | Completed Day 7
3 | WINDOW |  | add view menu to menubar | Completed Day 7
4 | WINDOW |  | add new course and new section to insert menu and course and section to view menu | Completed Day 7
5 | SUBJECT |  | code subject.h and subject.cpp | Completed Day 7
6 | COURSE |  | Write on_new_course_click using EntryDialog | Completed Day 7
7 | SECTION |  | Write on_new_section_click using EntryDialog | Completed Day 7
8 | WINDOW |  | update Makefile | Completed Day 7
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2021-04-13 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-04-20
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 4
Day 1 Left | 4 | 0
Day 2 Left | 4 | 0
Day 3 Left | 4 | 0
Day 4 Left | 4 | 0
Day 5 Left | 4 | 0
Day 6 Left | 1 | 3
Day 7 Left | 1 | 0
ADD tasks below to complete each feature for THIS sprint
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | TEACHER |  | code teacher.h and teacher.cpp | In Work
2 | GRADE |  | code enum class grade.h and grade.cpp | Completed Day 6
3 | TRANSCRIPT |  | code transcript.h and transcript.cpp | Completed Day 6
4 | ITERATORS |  | add iterators to student.h and parent.h | Completed Day 6
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84